## Gating Overview
Field | Example
Expansion Phase | Wave 2 – Midwest depots
Region / Site | Chicago, Indianapolis, St. Louis
Review Date | 2025-11-05
Gating Review Led By | Fleet Strategy & Infrastructure PM
Participants | Procurement, Fleet Ops, OEM, Site Managers
Decision Authority | Regional SteerCo
Objective | Validate infrastructure, vehicle, and operational readiness prior to release of new EV orders
Next Review | 2 weeks before scheduled OEM handover

## Readiness Checklist
Category | Check Item | Readiness Question | Evidence / Reference | Owner | Weight (%) | Status (Y/P/N) | Score (Auto) | Remarks
1. Technical & Infrastructure | Grid connection secured | Is contracted grid capacity ≥ forecast EV load (with margin)? | Grid Readiness Checklist | Infrastructure Lead | 10 | Y | 10 |  | Y
| Chargers installed & tested | Have all chargers passed commissioning & SoC data validation? | Commissioning report | CPO / Infra PM | 10 | Y | 10 |  | P
| Permits & safety clearance | Have all local electrical/HSE permits been received? | Permit Tracker | HSE | 8 | P | 4 |  | N
| Backup power & contingency | Is fallback power (battery/diesel) defined for critical sites? | Site Layout Plan | Ops | 4 | Y | 4
2. Vehicle & OEM Readiness | OEM delivery confirmed | Are vehicle VINs & ETA confirmed and matched to depot capacity? | OEM Delivery Sheet | Procurement | 8 | N | 0
| Telematics integration complete | Are EVs linked to fleet dashboards with SoC reporting tested? | Data & Systems Checklist | Fleet IT | 6 | N | 0
| Route suitability verified | Do assigned routes align with range, payload, and dwell window? | Route Analysis Tool | Fleet Ops | 8 | Y | 8
3. Operations & People | Driver training completed | Have all assigned drivers completed EV training & sign-off? | Training Records | Ops / HSE | 8 | Y | 8
| SOPs & fault protocols updated | Are local SOPs updated for charging, downtime, and escalation? | Charging SOP | Operations | 6 | Y | 6
| Depot operations readiness | Are depot schedules, parking layouts, and MHE workflows adjusted? | Site Readiness Audit | Depot Manager | 6 | P | 3
4. Data & Reporting | KPI dashboard live | Are uptime, utilization, and CO₂ KPIs visible before launch? | CO₂ Dashboard | Data Team | 5 | Y | 5
| Dummy data test passed | Were dummy charging runs conducted to confirm data flow? | Pilot Data Test | Data Lead | 4 | P | 2
5. Safety & Compliance | Site safety audit complete | Has a pre-launch HSE audit been conducted? | HSE Audit Report | HSE | 5 | Y | 5
| Emergency response tested | Are emergency and fault recovery drills completed? | Training Logs | HSE / Ops | 4 | Y | 4
6. Commercial & Customer | Contract alignment complete | Are CPO, OEM, and fleet contracts aligned with scaling terms? | Procurement Tracker | Legal / Procurement | 5 | N | 0
| Customer communication ready | Have customers been briefed on service adjustments? | Customer Brief Template | Product / Commercial | 3 | N | 0

## Scoring & Decision Summary
Metric | Formula (Excel) | Description
Total Weighted Score | 69 | Sum of all achieved weights
Max Possible Score | 100 | Sum of all item weights
Overall Readiness (%) | 69% | Overall readiness percentage
Decision Output | HOLD | Decision rule based on readiness %

## Action Tracker
Action ID | Linked Check | Action Description | Owner | Target Date | Status (Open/Closed) | Remarks
A-01 | Grid connection | Increase transformer capacity application | Infra Lead | 2025-11-20 | Open | Pending utility response
A-02 | Emergency drills | Conduct EV fire protocol dry-run | HSE | 2025-11-15 | Open | Planned with OEM support
A-03 | SOP update | Include new downtime reporting logic | Ops | 2025-11-18 | Closed | SOP updated 02-Nov-25