## Sheet1
|  | Internal Stakeholders | [10 empty] | External Stakeholders
| Task | Procurement | Product | Operations | Warehouse Eng. | PMO | Finance | Sustainability | HSSE | Legal | Marketing | Sales | OEMs | Utilities | CPOs
1.0 Planning (Steps 1.1-1.5) | 1. Assemble project team & define governance | C | A | C | C | R | C | C | C | C | I | I | I | I | I
| 2. Conduct route mapping & duty cycle analysis | I | C | R | I | C | I | I | I | I | I | C | C | C | I
| 3. Assess fleet utilization & vehicle suitability | I | C | R | I | C | I | I | I | I | I | C | C | C | I
| 4. Determine charging infrastructure requirements | I | I | C | R | C | I | I | C | I | I | I | C | C | R
| 5. Select preliminary vehicle & infra specifications | C | I | C | C | C | I | I | I | I | I | I | R | C | C
| 6. Conduct asset ownership assessment (lease vs. buy) | R | C | I | I | C | A | C | I | I | I | I | C | I | I
| 7. Develop Investment Proposal (IP) | C | C | C | I | C | A | C | I | I | I | I | I | I | I
| 8. Build TCO model (diesel vs EV) | C | C | C | I | C | A | C | I | I | I | I | I | I | I
| 9. Estimate emission reductions | I | I | I | I | I | C | R | I | I | I | I | I | I | I
| 10. Secure funding, incentives, subsidies | C | I | I | I | C | A | C | I | R | I | I | I | I | I
| 11. Develop project charter | C | C | C | C | R | C | C | C | I | I | I | I | I | I
| 12. Conduct risk assessment & mitigation | C | C | C | C | R | C | C | A | I | I | I | I | I | I
| 13. Engage internal & external stakeholders | C | C | C | C | R | I | I | I | I | A | C | R | R | R
2.0 Implementation (2.1-2.6) | 14. Conduct RFQs for EV trucks | R | I | I | I | C | I | I | I | I | I | I | C | I | I
| 15. Finalize vehicle specifications & contracts | R | C | C | I | C | I | I | I | A | I | I | R | I | I
| 16. Conduct RFQs for charging infrastructure | R | I | I | C | C | I | I | I | I | I | I | I | C | R
| 17. Finalize charging infra specs & contracts | R | I | C | C | C | I | I | I | A | I | I | I | R | R
| 18. Conduct site assessments for charging | C | I | C | R | C | I | I | I | I | I | I | C | R | R
| 19. Obtain permits & confirm grid upgrades | C | I | I | R | C | I | I | I | A | I | I | C | R | R
| 20. Set up data collection & reporting | I | I | R | I | C | C | C | I | I | I | I | I | I | I
| 21. Deliver training (drivers, techs, HSSE) | C | I | R | I | C | I | I | A | I | I | I | C | I | I
| 22. Set up financial tracking | C | I | I | I | C | R | I | I | I | I | I | I | I | I
3.0 Execution (3.1-3.4) | 23. Deploy & commission charging infrastructure | C | I | I | R | C | I | I | I | I | I | I | C | R | R
| 24. Commission EV trucks (testing) | C | I | R | I | C | I | I | I | I | I | I | R | I | I
| 25. Integrate EVs into fleet mgmt. systems | I | I | R | I | C | I | I | I | I | I | I | C | I | I
| 26. Establish charging schedules & load mgmt. | C | I | R | I | C | I | I | I | I | I | I | C | R | R
| 27. Monitor KPIs (energy, uptime, efficiency) | I | I | R | I | C | C | C | I | I | I | I | I | I | I
| 28. Collect driver feedback & lessons learned | I | I | R | I | C | I | I | I | I | I | I | I | I | I
| 29. Refine operational processes | I | I | R | I | C | I | I | I | I | I | C | C | I | I
4.0 Scaling (Steps 4.1-4.5) | 30. Refine scaling strategy | C | A | C | C | R | C | C | I | I | I | I | C | C | C
| 31. Secure approval for scaling plan | C | I | I | I | R | A | C | I | I | I | I | I | I | I
| 32. Expand EV fleet & infra deployment | R | C | C | C | C | I | I | I | I | I | I | C | C | C
| 33. Optimize logistics (utilization, routes) | I | I | R | I | C | I | I | I | I | I | C | I | I | I
| 34. Continuous improvement processes | I | I | R | I | C | C | C | I | I | I | I | I | I | I
| 35. Align ongoing reporting (sustainability) | I | I | R | I | C | C | A | I | I | I | I | I | I | I