## Master Plan
[22 empty] | Today | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-26 | 2025-05-27 | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X | Week X
50
[6 empty] | RESOURCE - RESPONSIBILITY ASSIGNMENT MATRIX (RAM) | [13 empty] | Risk | [77 empty] | Update/Comments | Update/Comments | Update/Comments | Update/Comments | Update/Comments
Type |  | Action | Critical Path | Duration | Created date | PROCUREMENT | PRODUCT | OPERATIONS | WAREHOUSE ENG. | PMO | FINANCE | SUSTAINABILITY | HSSE | LEGAL | MARKETING | SALES | OEMS | UTILITIES | CPOs | ⚠ Common Risks | Progress status | % | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | [38 empty] | Week X | Week X | Week X | Week X | Week X
[60 empty] | Progress Bar | [37 empty] | (WC - XX-XX) | (WC - XX-XX) | (WC - XX-XX) | (WC - XX-XX) | (WC - XX-XX)
P | 1 | PLANNING
G |  | * Establish operational, commercial, and financial feasibility; align stakeholders on scope and resourcing.
T | 1.1 | Initiation |  | 1 week |  | C | A | C | C | R | C | C | C | C | I | I | I | I | I |  | Not Started | 0%
ST |  | Assemble cross-functional team |  |  |  | C | A | C | C | R | C | C | C | C | I | I | I | I | I | Missing key functions (e.g. sustainability or operations) slows alignment | Ongoing | 50%
ST |  | Define roles and governance (RACI) |  |  |  | C | A | C | C | R | C | C | C | C | I | I | I | I | I |  | Completed | 100%
ST |  | Host alignment workshops |  |  |  | C | A | C | C | R | C | C | C | C | I | I | I | I | I | Ambiguity in ownership leads to duplicated or dropped tasks
M |  | Project charter kickoff | bar: C C C C to I I I I
T | 1.2 | Logistics & Operational Planning |  | 2 week |  | I | C | R | I | C | I | I | I | I | I | C | C | C | I
ST |  | Conduct fleet and route analysis |  |  |  | I | C | R | I | C | I | I | I | I | I | C | C | C | I | Poor data leads to inaccurate energy needs and misaligned specs
ST |  | Perform duty cycle modelling |  |  |  | I | C | R | I | C | I | I | I | I | I | C | C | C | I | Incorrect assumptions reduce service reliability or battery performance
ST |  | Plan charging infrastructure requirements |  |  |  | I | I | C | R | C | I | I | C | I | I | I | C | C | R | Under- or over-sizing leads to cost or performance issues
ST |  | Right-size vehicle specs (range, payload) |  |  |  | C | I | C | C | C | I | I | I | I | I | I | R | C | C | Specs do not match route conditions or site access
D |  | Completion of team setup and roles (1.1) | bar: C C C C to I I I I
M |  | Grid and routing feasibility confirmed | bar: C C C C to I I I I
T | 1.3 | Business Case Development |  | 2 week |  | C | C | C | I | C | A | C | I | I | I | I | I | I | I
ST |  | Build TCO, P&L, and IRR models |  |  |  | C | C | C | I | C | A | C | I | I | I | I | I | I | I | Cost inputs are inaccurate, leading to failed ROI expectations
ST |  | Estimate CO₂ reduction using standardised carbon framework |  |  |  | I | I | I | I | I | C | R | I | I | I | I | I | I | I | Wrong EF source leads to incorrect CO₂ claims or failed audits
ST |  | Define asset ownership and delivery model |  |  |  | R | C | I | I | C | A | C | I | I | I | I | C | I | I | Lack of ownership clarity complicates contracting and cost recovery
ST |  | Draft business case using standard template |  |  |  | C | C | C | I | C | A | C | I | I | I | I | I | I | I | Business case lacks detail or rigour and fails
ST |  | Validate emissions and commercial scenarios |  |  |  | C | C | C | I | C | A | C | I | I | I | I | I | I | I
D |  | Route/duty cycle data and asset requirements (1.2) | bar: R to I
M |  | Business case signed off | bar: R to I
T | 1.4 | Project Plan |  | 1 week |  | C | C | C | C | R | C | C | C | I | I | I | I | I | I
ST |  | Develop and finalize project charter |  |  |  | C | C | C | C | R | C | C | C | I | I | I | I | I | I | Scope or delivery timelines are not clearly defined
ST |  | Define KPIs, milestone plan, and risks |  |  |  | C | C | C | C | R | C | C | A | I | I | I | I | I | I | Project lacks clear success criteria or risk visibility
ST |  | Set up escalation and issue-tracking framework |  |  |  | C | C | C | C | R | C | C | A | I | I | I | I | I | I | No escalation path results in unresolved issues delaying delivery
ST |  | Align stakeholders on delivery sequencing |  |  |  | C | C | C | C | R | I | I | I | I | A | C | R | R | R
D |  | Business case completion (1.3) | bar: C C C to I I C
M |  | Project plan approved | bar: C C C to I I C
P | 2 | IMPLEMENTATION
G |  | *Procure assets, prepare sites, and validate operational readiness
T | 2.1 | Vehicle Procurement |  | 2 week |  | R | I | I | I | C | I | I | I | I | I | I | C | I | I
ST |  | Issue RFQ and shortlist OEMs |  |  |  | R | I | I | I | C | I | I | I | I | I | I | C | I | I | Delays in contracting cause vehicle lead time to slip
ST |  | Confirm technical specs |  |  |  | R | C | C | I | C | I | I | I | A | I | I | R | I | I | Incorrect specs ordered; delivery mismatch
ST |  | Sign service contracts and delivery agreements |  |  |  | R | C | C | I | C | I | I | I | A | I | I | R | I | I
D |  | Business case and project charter approved (1.4) | bar: R R to I I
M |  | Vehicle order confirmed | bar: R R to I I
T | 2.2 | Infrastructure Procurement |  | 3 week |  | R | I | I | C | C | I | I | I | I | I | I | I | C | R
ST |  | Issue RFQ for CPO or charging hardware |  |  |  | R | I | I | C | C | I | I | I | I | I | I | I | C | R | Commercial terms misaligned with delivery timeline
ST |  | Finalize layout, charger type, and power needs |  |  |  | R | I | C | C | C | I | I | I | A | I | I | I | R | R | Grid capacity not confirmed in time; permits blocked
ST |  | Confirm grid capacity and apply for upgrades |  |  |  | C | I | I | R | C | I | I | I | A | I | I | C | R | R
D |  | Completion of 1.2 and 1.4 | bar: R C to I I
M |  | Charger specs and site layout locked | bar: R C to I I
T | 2.3 | Site Readiness & Permits |  | 6 week |  | C | I | I | R | C | I | I | I | A | I | I | C | R | R
ST |  | Secure all construction and electrical permits |  |  |  | C | I | I | R | C | I | I | I | A | I | I | C | R | R | Permit delays cause construction hold-ups
ST |  | Schedule civil and electrical works |  |  |  | C | I | I | R | C | I | I | I | A | I | I | C | R | R | Civil works not coordinated with charger delivery
ST |  | Confirm timeline with grid operator and landlord |  |  |  | C | I | I | R | C | I | I | I | A | I | I | C | R | R
D |  | Infrastructure plan approved (2.2) | bar: C C C C to I I I I
M |  | Site cleared for installation | bar: C C C C to I I I I
T | 2.4 | Data & Systems Setup |  | 2 week |  | I | I | R | I | C | C | C | I | I | I | I | I | I | I
ST |  | Configure telematics for EVs |  |  |  | I | I | R | I | C | C | C | I | I | I | I | I | I | I | Telematics system incompatible or delayed integration
ST |  | Set up charging platform and backend integration |  |  |  | I | I | R | I | C | C | C | I | I | I | I | I | I | R | No visibility into charging events for performance tracking
ST |  | Link reporting tools to TCO and carbon dashboard |  |  |  | C | I | I | I | C | R | I | I | I | I | I | I | I | I
D |  | Final vehicle and charger specs (2.1, 2.2) | bar: I I I I
M |  | Data and monitoring systems operational | bar: I I I I
T | 2.5 | Training & Onboarding |  | 1 week |  | C | I | R | I | C | I | I | A | I | I | I | C | I | I
ST |  | Deliver driver and safety training |  |  |  | C | I | R | I | C | I | I | A | I | I | I | C | I | I | Inadequate EV training increases risk of improper use
ST |  | Review emergency protocols and site access |  |  |  | C | I | R | I | C | I | I | A | I | I | I | I | I | I | Lack of protocols increases response time in incidents
ST |  | Prepare SOP for charging operations |  |  |  | C | I | R | I | C | I | I | A | I | I | I | I | I | R
D |  | Staff identified in charter (1.4); site readiness confirmed (2.3) | bar: I I I I
M |  | Operational team EV-ready | bar: I I I I
P | 3 | EXECUTION | bar: I I I I to I I I R
ST |  | *Deploy assets and validate operational performance under real conditions. |  |  |  | C | I | I | R | C | I | I | I | I | I | I | C | R | R
ST | 3.1 | Infrastructure Commissioning |  | 1 week |  | C | I | I | R | C | I | I | I | I | I | I | C | R | R
ST |  | Install and test chargers |  |  |  | C | I | I | R | C | I | I | I | I | I | I | C | R | R | Hardware fails commissioning or doesn't meet uptime targets
ST |  | Validate load management and uptime |  |  |  | C | I | I | R | C | I | I | I | I | I | I | C | R | R | Schedules don’t align with route needs
ST |  | Run energy balancing scenarios |  |  |  | C | I | I | R | C | I | I | I | I | I | I | C | R | R
D |  | Site readiness complete (2.3), system setup (2.4) | bar: I I I I
M |  | Infrastructure live and certified | bar: I I I I
T | 3.2 | Vehicle Deployment |  | 1 week |  | C | I | R | I | C | I | I | I | I | I | I | R | I | I
ST |  | Register and test Evs |  |  |  | C | I | R | I | C | I | I | I | I | I | I | R | I | I | Registration delays or failed inspection prevent deployment
ST |  | Integrate Evs into fleet mgmt. systems |  |  |  | I | I | R | I | C | I | I | I | I | I | I | C | I | I
ST |  | Establish charging schedules and load mgmt. |  |  |  | C | I | R | I | C | I | I | I | I | I | I | C | R | R
ST |  | Assign to operational routes |  |  |  | C | I | R | I | C | I | I | I | I | I | I | R | I | I | Misassigned vehicles underperform or delay service
ST |  | Monitor charging schedule alignment |  |  |  | C | I | R | I | C | I | I | I | I | I | I | R | I | I
D |  | Vehicle delivery confirmed (2.1) | bar: I I I I
M |  | Vehicles deployed | bar: I I I I
T | 3.3 | Pilot Monitoring |  | 6 week |  | I | I | R | I | C | C | C | I | I | I | I | I | I | I
ST |  | Track KPIs: TCO, uptime, SG&A, range, charging |  |  |  | I | I | R | I | C | C | C | I | I | I | I | I | I | I | Inconsistent data feeds impair tracking and decisions
ST |  | Log operational anomalies |  |  |  | I | I | R | I | C | I | I | I | I | I | C | C | I | I
ST |  | Collect driver and customer feedback |  |  |  | I | I | R | I | C | I | I | I | I | I | I | I | I | I | Feedback not collected or used to improve operations
D |  | Vehicles and chargers in use (3.1, 3.2) | bar: I I I I
M |  | Pilot performance report completed | bar: I I I I
T | 3.4 | Operational Handover |  | 1 week |  | I | I | R | I | A | C | C | I | I | I | I | I | I | I
ST |  | Summarise lessons learned |  |  |  | I | I | R | I | A | C | C | I | I | I | I | I | I | I | Key learnings not captured, leading to repeated mistakes
ST |  | Document KPI compliance |  |  |  | I | I | R | I | A | C | C | I | I | I | I | I | I | I | Pilot fails to meet minimum thresholds for scaling
ST |  | Hold internal and external stakeholder review |  |  |  | I | I | R | I | A | C | C | I | I | I | I | I | I | I
ST |  | Refine Operational processes
D |  | Pilot data collection complete (3.3) | bar: I I I I
M |  | Handover complete, Go/No-Go for scaling | bar: I I I I
P | 4 | SCALING | bar: I I I I to I I I I
G |  | *Expand EV fleet and infrastructure while optimizing operations and cost.
T | 4.1 | Scaling Plan Finalization |  | 1 week |  | C | A | C | C | R | C | C | I | I | I | I | C | C | C | Pilot results not reflected in updated strategy
ST |  | Update plan based on pilot outcomes |  |  |  | C | A | C | C | R | C | C | I | I | I | I | C | C | C | Budget underestimates costs or timeline misalignment
ST |  | Secure extended funding and approvals |  |  |  | C | I | I | I | R | A | C | I | I | I | I | I | I | I
D |  | Pilot handover completed (3.4) | bar: I I I
M |  | Scaling plan signed off | bar: I I I
T | 4.2 | Fleet Expansion |  | 4 week per cycle |  | R | C | C | C | C | I | I | I | I | I | I | R | C | C
ST |  | Place follow-up vehicle orders |  |  |  | R | C | C | C | C | I | I | I | I | I | I | R | C | C | Delayed procurement affects scaling timeline
ST |  | Expand depot or route coverage |  |  |  | R | C | C | C | C | I | I | I | I | I | I | C | C | C | New sites not ready or staffed
D |  | Scaling plan approved (4.1) | bar: I I I
M |  | Additional EVs deployed | bar: I I I
T | 4.3 | Infrastructure Expansion |  | 3 week per site |  | R | C | C | C | C | I | I | I | I | I | I | C | C | R
ST |  | Add chargers at new sites |  |  |  | R | C | C | C | C | I | I | I | I | I | I | C | C | R | Charger upgrades do not meet higher load demand
ST |  | Explore en-route solutions |  |  |  | R | C | C | C | C | I | I | I | I | I | I | C | C | C | Infrastructure not permitted or cost prohibitive
D |  | Scaling plan and utility readiness (4.1) | bar: I I I
M |  | Additional sites electrified | bar: I I I
T | 4.4 | Continuous Improvement |  | ongoing |  | I | I | R | I | C | C | A | I | I | I | I | I | I | I
ST |  | Review emissions and utilization monthly |  |  |  | I | I | R | I | C | C | A | I | I | I | I | I | I | I | CO₂ data not trusted or not tied to operational activity
ST |  | Adjust shift schedules and charging plans |  |  |  | I | I | R | I | C | I | I | I | I | I | C | I | I | I | Utilization falls short due to poor route design
ST |  | Engage customers with CO₂ performance updates |  |  |  | I | R | I | I | I | C | C | I | I | C | R | I | I | I
D |  | Data systems established in 2.4 | bar: I I to I I
M |  | First-year emissions report delivered | bar: I I to I I