## Cover and Instructions
Purpose
This checklist supports decision-making between Pilot Completion (Phase 3) and Scale-Up (Phase 4). All items should be verified with supporting evidence before requesting a Go decision.
How to use
Mark each criterion as Yes / Partial / No.
Provide evidence link or reference.
Items marked “No” must include mitigation plan or follow-up action.
Minimum Criteria
All “Critical” items = “Yes”, and total Go score ≥ 80%

## Go_No-Go Checklist
Category | Evaluation Criterion | Status (Yes/Partial/No) | Weighted score | Evidence / Link | Comments / Mitigation | Priority | Status weight
1. Technical Readiness | Chargers commissioned and tested under load (≥ 95% uptime) | Yes | 2 | [SharePoint link] |  | Critical | Yes | 1
| Vehicles reporting SOC, energy, and utilisation to dashboards | Partial | 1 |  |  | Critical | Partial | 0.5
| OEM telematics integrated with KPI dashboard | No | 0 |  |  | High | No | 0
| Energy efficiency within ±10% of design assumption (kWh/km) | Yes | 1 |  |  | High
| Grid capacity sufficient for projected fleet + 20% margin | Partial | 0.5 |  |  | High
2. Operational Readiness | Drivers trained and certified on EV SOPs | No | 0 | [link] |  | Critical
| Charger SOPs tested (incl. escalation paths) | Yes | 1 |  |  | High
| Site maintenance procedures updated | Partial | 0.5 |  |  | Medium
| Uptime > 95% during last 4 weeks | No | 0 |  |  | High
| Range or charging issues resolved | Yes | 1 |  |  | High
3. Data & Reporting | Carbon reporting framework (ISO 14083 / SFC) validated | Partial | 1 |  |  | Critical
| TCO model updated with pilot data | No | 0 |  |  | High
| KPI dashboard functional and verified | Yes | 1 | [link] |  | High
| 100% of vehicles feeding data | Partial | 1 |  |  | Critical
4. Safety & Compliance | HSE approval for EV operations (fire, charging zones) | No | 0 |  |  | Critical
| Incident logs reviewed, mitigations closed | Yes | 1 |  |  | High
5. Commercial Readiness | Supplier contracts include SLA and uptime clauses | Partial | 0.5 |  |  | High
| Charging cost variance within ± 10% of forecast | No | 0 |  |  | Medium
| Depot/route expansion plan validated by Procurement | Yes | 1 |  |  | High
6. Learnings & Feedback | Lessons-learned workshop completed | Partial | 0.5 |  |  | Medium
| SOPs and training updated based on pilot learnings | No | 0 |  |  | High
| Customer feedback collected and addressed | Yes | 1 |  |  | Medium
7. Decision Summary | All Critical = “Yes”; Go score ≥ 80% |  |  | — | — | —
Overall Go Score | 50%

## Evidence Log
Ref ID | Category | Description | File / Folder Link | Owner | Verified By | Date
E-01 | Technical | Charger load test results | [SharePoint link] | Site Eng. | Fleet Ops | 2025-11-01
E-02 | Operational | Driver training register | [link] | Ops | HSSE | 2025-11-03
E-03 | Data | KPI dashboard screenshot | [link] | Carbon Lead | PMO | 2025-11-04

## Summary Dashboard
Overall Go Score (%) | 50%
Critical path items not met | Vehicles reporting SOC, energy, and utilisation to dashboards
OEM telematics integrated with KPI dashboard
Grid capacity sufficient for projected fleet + 20% margin
Drivers trained and certified on EV SOPs
Site maintenance procedures updated
Uptime > 95% during last 4 weeks
Carbon reporting framework (ISO 14083 / SFC) validated
TCO model updated with pilot data
100% of vehicles feeding data
HSE approval for EV operations (fire, charging zones)
Supplier contracts include SLA and uptime clauses
Charging cost variance within ± 10% of forecast
Lessons-learned workshop completed
SOPs and training updated based on pilot learnings