## Overview and Instructions
Field | Example
Project / Pilot ID | NAM-EV01
Depot / Site | Chicago Rail Hub
Period Covered | Oct–Nov 2025
Total Vehicles | 10
Vehicle Types | Volvo FM, Freightliner eCascadia
Primary Objective | Validate range, uptime, and grid performance
Report Compiled By | Fleet Ops / Energy Transition
Date | 2025-12-05
Instructions
Record all key insights, issues, and learnings per category.
Focus on what happened, why, and what we’ll do differently.
Use concise, factual language — avoid blame, emphasize process improvement.
Lessons” should be actionable and ideally link to an SOP or future planning step.

## Lessons Log
Category | Theme | Observation / Event | Root Cause | Impact (H/M/L) | Lesson Learned | Recommended Action | Responsible Function | Related Tool / SOP | Status
Technical | Charger reliability | 3 DC units offline during heatwave | Cooling fan firmware fault | High | Charger derates above 35°C | Validate thermal tests before procurement | Technical Lead | Charging SOP | Closed | Technical
Operational | Shift overlap | Drivers competing for chargers 05:00–06:00 | Poor scheduling overlap | Medium | Need staggered shift plan | Adjust route and shift alignment | Fleet Ops | Charging Schedule Planner | Open | Operational
Data | Telematics missing data | EV-003 not sending range updates | API connection lost | Medium | OEM integration incomplete | Implement daily API data quality check | Data Lead | KPI Tracker | Closed | Data
Safety | Charger reset during charge | Operator restarted without PPE | Insufficient training | High | Charging restart SOP missing | Update HSE training | HSE / Training | Charging SOP | Open | Safety
Commercial | Energy cost deviation | Site tariff higher than model | Missed TOU optimization | Medium | Review load management config | Enable off-peak charging automation | Procurement / Facilities | Load Forecast Tool | Planned | Commercial
Customer | Feedback from carrier | Carriers hesitant on new process | Low awareness | Low | Co-create training content with carriers | Host joint training sessions | Product / Procurement | Driver Training SOP | Planned | Customer
High
Medium
Low
Open
Closed
Planned

## Root cause & Mitigation reg.
Category | Issue Summary | Root Cause | Mitigation Applied | Result | Recurrence Risk (H/M/L) | Owner
Technical | Charger derating | OEM firmware not updated | Vendor patch applied | Stable | L | Technical Lead | H
Data | Missing telematics data | Token expiry | Automated API token renewal | Resolved | L | Data Engineer | M
Operational | Driver SOC variance | Unclear SOP | Retrained 5 operators | Improving | M | Ops Supervisor | L

## Improvement actions tracker
Action ID | Description | Linked Lesson | Responsible | Target Date | Status | Evidence / Link
A-01 | Update Charging SOP to include heat stress limits | Technical #1 | Energy Transition | 2025-01-15 | Open | [SharePoint Link]
A-02 | Create API health dashboard | Data #3 | IT / Data | 2025-12-10 | Closed | [link] | Open
A-03 | Adjust shift schedule to avoid overlap | Operational #2 | Fleet Ops | 2025-12-05 | Closed | [link] | Planned
Closed

## Summary dashboard
Category | # Lessons | % Closed | % High Impact | Common Themes
Technical | 1 | 100% | 100% | Charger reliability
Operational | 1 | 0% | 0% | Shift overlap
Data | 1 | 100% | 0% | Telematics missing data
Safety | 1 | 0% | 100% | Charger reset during charge
Commercial | 1 | 0% | 0% | Energy cost deviation
Total Lessons | 6
% Closed Overall | 33.33%
% High Impact Overall | 33.33%
Top recurring issues | Charger reliability | 1
| Shift overlap | 1
| Telematics missing data | 1
| Charger reset during charge | 1
| Energy cost deviation | 1
| Feedback from carrier | 1