## Sheet1
[6 empty] | Initiation | Logistics and Operational planning | Business case Development | Project Planning | EV Truck Procurement | Infrastructure Procurement | Site readiness and permitting | Data collection and systems integration | Training and onboarding | Financial planning and cost tracking | Infrastructure Commissioning | Vehicle Deployment | Pilot Monitoring | Operational Handover | Scaling plan finalisation | Fleet expansion | Infrastructure expansion | Continuous Improvement | Cross-Task
| Tool/ Template | Description | Maersk Only | Link | Development status | 1.1 | 1.2 | 1.3 | 1.4 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 3.1 | 3.2 | 3.3 | 3.4 | 4.1 | 4.2 | 4.3 | 4.4
T1 | Project Charter Template | Defines scope, roles, risks, and governance |  | link | ✅ | [18 empty] | ✅ | bar: 1.1; 1.4
T2 | RACI Matrix | Clarifies roles and responsibilities across stakeholders |  | link | ✅ | [18 empty] | ✅ | bar: 1.1; 1.4
T3 | Route Analysis Template | Maps routes, range, terrain, and charging needs |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.1; 4.2
T4 | Fleet Utilisation Assessment Tool | Assesses distance, shift windows, idle time, and EV readiness |  | link | ✅ | [18 empty] | ✅ | bar: 1.2 to 1.3; 4.1
T5 | Vehicle OEM Catalogue (Specs Reference) | Compares battery, range, payload specs |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.1
T6 | Charging Infrastructure Guidelines | Details site, power, and charger planning |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.2 to 2.3; 3.1; 4.3
T7 | Charging Infrastructure OEM catalogue |  |  | link | ✅ | bar: 2.2; 3.1
T8 | Grid Readiness Checklist | Validates grid capacity, utility engagement |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.2 to 2.3; 3.1; 4.3
T9 | TCO Model (Standardised) | Calculates cost per km/ton, OPEX/CAPEX tradeoffs |  | link | ✅ | [18 empty] | ✅ | bar: 1.3; 2.6; 3.3; 4.1
T10 | Carbon Reporting Framework (SFC/ISO) | Tracks emissions in scope-aligned, SBTi-compliant format |  | link | ✅ | [18 empty] | ✅ | bar: 1.3; 2.4; 3.3; 4.4
T11 | KPI Tracker | Monitors uptime, energy use, efficiency, utilization |  | link | ✅ | [18 empty] | ✅ | bar: 3.3 to 3.4; 4.4
T12 | Charging SOP | Explains safe and efficient charging processes |  | link | ✅ | [18 empty] | ✅ | bar: 2.5; 3.1
T13 | Driver Training Checklist | Confirms driver onboarding on EV usage |  | link | ✅ | [18 empty] | ❌ | bar: 2.5
T14 | Vehicle readiness checklist | Confirms truck registration, range testing, telematics, and handover |  | link | ✅ | [18 empty] | ❌ | bar: 3.2
T15 | Route assignment tracker | Maps EVs to specific duty cycles and shifts |  | link | ✅ | [18 empty] | ❌ | bar: 3.2
T16 | Go/No-Go Review Template | Formalizes scaling readiness and pilot evaluation |  | link | ✅ | [18 empty] | ❌ | bar: 3.4
T17 | Scaling Plan Template | Consolidates strategy for phased deployment |  | link | ✅ | [18 empty] | ❌ | bar: 4.1
T18 | Deployment Gating Checklist | Aligns vehicle delivery with infrastructure and readiness |  | link | ✅ | [18 empty] | ❌ | bar: 4.2
T19 | Load Management Forecast Tool | Models peak power vs. charging needs |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.1; 4.2 to 4.3
T20 | Lessons Learned Template | Captures insights from pilot phase |  | link | ✅ | [18 empty] | ✅ | bar: 3.4 to 4.1
T21 | EV Business Plan template | Standardised internal template for evaluating EV investment proposals, including operational assumptions, infrastructure scope, financials, and risk assessment. |  | link | ✅ | [18 empty] | ✅ | bar: 1.3; 2.6
T22 | EV Deployment Master Project Plan | High-level project plan covering milestones, dependencies, stakeholders, and timelines across vehicle, infrastructure, and operational readiness streams |  | link | ✅ | [18 empty] | ✅ | bar: 1.4; 2.3; 3.1
T23 | Data collection template | Standard template for collecting vehicle, energy, charging, uptime, and operational data during pilot and early deployment phases to support KPI tracking and lessons learned. |  | link | ✅ | [18 empty] | ✅ | bar: 2.4; 3.3; 4.4
T24 | Site assessment template | Structured checklist and data capture tool to assess site electrical capacity, layout constraints, permitting readiness, and charging feasibility prior to infrastructure design. |  | link | ✅ | [18 empty] | ✅ | bar: 1.2; 2.3
T25 | Permitting and site preperation SOP | Step-by-step SOP outlining permitting pathways, utility engagement, site preparation activities, and typical lead times for EV charging infrastructure projects. |  | link | ✅ | [18 empty] | ✅ | bar: 2.2 to 2.3
T26 | Charging Schedule Planner | Simple planning tool to allocate charging windows across vehicles based on dwell time, charger availability, and operational constraints. |  | link | ✅ | [18 empty] | ✅ | bar: 3.2 to 3.3
T27 | Charging Schedule Simulation tool | Time-step simulation tool to model vehicle state-of-charge, driving consumption, opportunity charging, and overnight charging under real operational schedules. |  | link | ✅ | [18 empty] | ✅ | bar: 3.2 to 3.3; 4.1
T28 | Scaling lessons learned debrief | Structured debrief template to capture operational, technical, commercial, and organisational learnings during scaling phases beyond initial pilots. |  | link | ✅ | [18 empty] | ✅ | bar: 4.2; 4.4
T29 | TBM Cockpit | Internal performance and cost cockpit aggregating fleet KPIs, energy use, emissions, and financial metrics across deployments. | Yes | link | ✅ | [18 empty] | ✅ | bar: 2.6; 4.4
| EV HDT Maturity curve for First mile |  |  | "C:\Users\JHA438\OneDrive - Maersk Group\02 Standards & Innovation\03 Projects\2. EV Deployment Guidelines\EV HDT Maturity Curve for First-Mile Use (Mature Markets).xlsx"