## Slide 1: Permitting & Site Preparation SOP (v1.0)
Objective: To standardize the site readiness process for EV charger installation — ensuring all necessary utility, landlord, and regulatory permits are secured before commissioning begins.
Outcome: A “Ready for Installation” site with approved permits, validated grid capacity, and completed civil works.
Notes: This could be tied directly to the Gannt chart tool.
I think it would be better to keep the "Deliverables" out of this section. So, we convey carefully the function of each stage.
Or we'll have to think of different ways to manage the complexity of this section.

## Slide 2: Overview
Item | Description
Purpose | Define the step-by-step procedure for obtaining required permits, preparing sites, and validating readiness for charger installation.
Scope | Applies to all warehouse, depot, and terminal locations installing EV charging infrastructure.
Owner | Infrastructure Lead / Site Project Manager
Dependencies | 2.1 Site Readiness, 2.2 Procurement, and 3.1 Infrastructure Commissioning
Field | Example
Version | 1.1
Owner | Global Infrastructure Lead
Review Cycle | Annual or post-project
Next Review Date | Q4 2026

## Slide 3: Workflow
Step 1. Confirm Site Ownership & Key Contacts
Confirm physical site boundary, landlord ownership, and utility provider. Identify key contacts (landlord, CPO, grid operator, permitting office).
Responsible
Site Lead / Facility Manager
Output/ Evidence
Stakeholder register
Typical lead time
1 week
Step 2. Validate Electrical Capacity & Utility Connection
Confirm available kVA/kW, connection type (LV/MV), and utility process for capacity increase if needed.
Responsible
Utility Operator / Engineering
Output/ Evidence
Grid readiness checklist
Typical lead time
2–4 weeks
Step 3. Perform Site Layout & Safety Review
Map charger placement, trenching, safety clearances, and accessibility zones (truck, MHE, cars).
Responsible
Project Engineer / OEM
Output/ Evidence
Site layout drawing (preliminary)
Typical lead time
2 weeks
Step 4. Apply for Permits
Secure required documentation:
  Electrical installation permit
  Construction/trenching permit
  Landlord consent
  Environmental/HSE clearance
Responsible
Site Lead / General Contractor
Output/ Evidence
Submitted permit package
Typical lead time
4–12 weeks
Step 5. Track Permit Review & Closure
Track permit progress; coordinate with utilities and contractors to close gaps.
Responsible
Project Manager / Local Authority
Output/ Evidence
Permit approval letters
Typical lead time
2–8 weeks
Step 6. Execute Civil & Electrical Works
Execute civil and electrical works: trenching, conduit installation, protective bollards, signage.
Responsible
Contractor / Facilities
Output/ Evidence
Completion report / as-built drawings
Typical lead time
2–6 weeks
Examples:
EU: Building permit, DSO grid upgrade approval, environmental compliance notice.
US: AHJ electrical permit, trenching/construction permit, fire marshal sign-off.
APAC: Landlord consent, energy bureau approval, local council excavation permit.

## Slide 4: Common risks and mitigations
🚫 Permit delays due to incomplete submissions
Mitigation: Use standardized permit templates; submit all documents in one package..
🚫 Grid upgrade dependencies delay installation
Mitigation: Engage utility early (Step 2); request temporary load or phase installation.
🚫 Landlord not aligned on charger placement
Mitigation: Include site owner in Step 1 boundary review; share layout for approval.
.
🚫 Civil works conflict with site ops
Mitigation: Coordinate trenching during off-peak hours; use temporary barriers and phased work.
🚫 Documentation gaps at inspection
Mitigation: Store all permits, drawings, and safety certifications in central SharePoint folder.

## Slide 5: Go/No-Go Checklist
Checkpoint | Status
All permits approved (documented) | ☐
Utility confirmation of load availability | ☐
Civil and trenching works completed | ☐
Charger foundations and conduits installed | ☐
Safety barriers and signage installed | ☐
As-built drawings submitted | ☐
HSE inspection passed | ☐
“Ready for Installation” sign-off | ☐

## Slide 6: Approval Matrix
Permit Type | Responsible Party | Sign-Off Authority | Local Variations
Electrical Permit | Contractor → Site Lead | Utility / Grid Operator | Country-specific
Construction / Trenching | Contractor | Local Municipality | 
Environmental / HSE | HSE Lead | Local Environmental Authority | 
Landlord Consent | Project Manager | Landlord / Real Estate | 
Operational Safety | Site Manager | HSE & Ops |