## Overview & Scope
Field | Example
Scaling Phase | Phase 2 (2026 Rollout)
Region / Market | North America – Midwest
# of Sites | 4 depots
# of Vehicles | 60 e-trucks (Volvo, Freightliner)
# of Chargers | 35 DC, 10 AC
Reporting Period | Jan–Jun 2026
Scaling Objectives | Achieve 90% uptime, reduce energy cost 15%, establish regional grid partnerships
Report Compiled By | Energy Transition PM / Regional Decarbonisation Lead
Reviewed By | Global Electrification Steering Committee
Date | 2026-07-15

## Scaling Lessons Log
Category | Theme / Issue | Scaling Observation | Underlying Cause | Impact (H/M/L) | Lesson Learned | Recommended Action | Responsible Function | Region / Site | Evidence / Source | Status (Open/Closed) | Date Logged
Infrastructure | Grid upgrade delays | Permitting took 8–12 months longer than estimated | Utility coordination gaps | High | Early utility engagement critical | Initiate grid application at feasibility stage | Infrastructure / Procurement | Midwest (4 depots) | Utility correspondence | Open | 2026-05-10 | Infrastructure
Technical | Charger software mismatch | Two vendors not interoperable on OCPP | Platform fragmentation | High | Standardize on OCPP 1.6+ certified hardware | Update procurement specs | Infra / Tech | Midwest | Charger integration logs | Closed | 2026-04-22 | Technical
Operational | Depot scheduling conflicts | Sites running overlapping shifts | Lack of cross-site harmonization | Medium | Harmonize charging strategy across depots | Update Charging Schedule Planner SOP | Ops / Energy Transition | Midwest | Depot schedules | Planned | 2026-05-02 | Operational
Data | KPI dashboards not aligned | Sites reporting on different KPIs | No unified data schema | Medium | Establish central KPI data model | Revise reporting SOP, connect to CO₂ dashboard | Data / Reporting | Global | KPI tracker snapshots | Closed | 2026-06-01 | Data
Safety | Incident near charger plug | Driver bypassed lock-out tag | Procedure drift with contractors | High | Continuous re-training and supervision needed | Include EV refresher in annual safety training | HSE / Ops | Midwest | HSE audit | Closed | 2026-05-15 | Safety
Commercial | Energy tariff variation across sites | Large OPEX deviation (±25%) | No energy procurement alignment | High | Regional energy purchasing needed | Negotiate aggregated tariff with CPO | Procurement / Finance | Midwest | Utility bills | Open | 2026-05-28 | Commercial
Stakeholder | Vendor coordination inconsistent | OEM, CPO, and utility meetings unaligned | Lack of shared governance | Medium | Set up quarterly vendor council | Add governance cadence to Scaling SOP | Electrification PMO | Global | Meeting tracker | Open | 2026-06-12 | Stakeholder
High
Medium
Low
Open
Closed
Planned

## Systemic Root Cause Register
Recurring Theme | Root Cause | Cross-Site Evidence | Mitigation Applied | Owner | Result / Effectiveness | Recurrence Risk (H/M/L)
Permitting delays | Utility approvals and unclear roles | All 4 Midwest depots | Pre-application engagement | Infra Lead | Improved in Phase 3 | Medium
Data inconsistency | No shared KPI schema | 3 data sources using different formats | Central KPI model in Power BI | Data Lead | Pending rollout | Medium
Vendor misalignment | No shared governance cadence | 2 OEMs, 1 CPO | Quarterly joint calls | PMO | Improved visibility | Low | High
Medium
Low

## Scaling Improvement Action Trac
Action ID | Linked Lesson | Action Description | Owner | Target Date | Priority (H/M/L) | Status | Evidence / Link
A-01 | Early utility engagement critical | Add utility engagement to pre-feasibility checklist | Infra / Procurement | 2026-08-15 | High | Open | [Grid checklist]
A-02 | Establish central KPI data model | Define KPI schema for all scaling sites | Data / Reporting | 2026-07-31 | High | Planned | [Power BI spec] | High
A-03 | Harmonize charging strategy across depots | Align depot shift times regionally | Ops / Transition | 2026-09-01 | Medium | Planned | [Ops plan draft] | Medium
A-04 | Set up quarterly vendor council | Set up vendor governance meeting cadence | PMO | 2026-08-01 | Medium | Open | [Meeting minutes] | Low
Open
Planned
Closed

## Summary Dashboard
Category | # Lessons | % Closed | % High Impact | Top Theme
Infrastructure | 1 | 0 | 1 | Grid delays
Technical | 1 | 1 | 1 | Interoperability
Operational | 1 | 0 | 0 | Shift conflicts
Data & Reporting | 1 | 1 | 0 | KPI alignment
Safety & Training | 1 | 1 | 1 | Procedure drift
Commercial | 1 | 0 | 1 | Tariff variation
Stakeholder & Vendor | 1 | 0 | 0 | Coordination gaps
Overall Close Rate (%) | 42.86%