## Overview & Assumptions
Field | Example
Project / Region | NAM – Midwest Expansion
Scaling Phase | Phase 1 (2026)
Total Vehicles (Target) | 150
Charger Count (Target) | 80 DC + 20 AC
Pilot Reference | Pilot CHG-03 (Chicago Hub)
Scaling Objectives | Achieve > 90 % uptime, reduce energy cost by 15 %
Key Pilot Learnings Applied | 1) Staggered charging by shift, 2) Pre-commissioning dry-runs, 3) Telematics API validation

## Scaling Readiness Matrix
Category | Key Readiness Criteria | Evidence / Source | Owner | Status | Score (0–5) | Comments
Fleet & Technical | Vehicle specs validated for scaling (range, payload, duty cycles, OEM support confirmed) | OEM validation letter, telematics range data, pilot performance report | Fleet Tech Lead | 🟢 Ready | 5 | Same models used in pilot; OEM performance verified under full payload
Infrastructure | Grid capacity, permitting, and hardware scalability confirmed (including space for future expansion) | Utility capacity study, permit tracking log, site readiness checklist | Infrastructure Lead | 🟡 Partial | 3 | One substation upgrade pending; new DC units under procurement
Operational | Shift plans, route assignments, and charger allocation optimized for higher fleet density | Route & Duty Cycle Planner, Charger Schedule Plan | Operations Manager | 🟢 Ready | 5 | Shift staggering plan validated with fleet and warehouse teams
Data & Systems | Telematics and charging platform fully integrated with reporting dashboards (CO₂, uptime, TCO) | API test logs, CO₂ Dashboard validation report | Reporting / Data Lead | 🟢 Ready | 4 | API integration stable; auto-refresh still under test
Safety & Training | SOPs updated and training complete for scaled operation (drivers, technicians, warehouse staff) | Updated SOPs, training attendance log, HSE audit | HSE / Training Lead | 🟢 Ready | 5 | All staff trained and signed off on revised SOPs
Commercial & Procurement | Vendor frameworks, SLAs, and pricing updated for EV maintenance, charging, and uptime guarantees | Procurement framework, vendor SLA tracker | Procurement Lead | 🟡 Partial | 3 | Awaiting final SLA amendment with key CPO partner
Financial & Governance | Updated scaling business case, risk register, and SteerCo approval complete | Revised TCO Model, SteerCo minutes, Risk Register | Finance BP / Scaling PM | 🟢 Ready | 4 | Scaling CapEx approved; Opex still under validation
Score | Meaning
0–1 | Not started
2 | Early progress – limited documentation
3 | Partial readiness – dependencies open
4 | Mostly ready – minor refinements pending
5 | Fully validated and approved
Overall Readiness Calculation | 82.86%

## Fleet & Infra. Exp. Plan
Phase | Timeline | # Vehicles Added | # Chargers Added | Grid Upgrade Req’d | Key Sites / Routes | Dependencies | Responsible Owner | Status
Phase 1 | Q2 2026 | 50 | 25 | No | Midwest Hub → Chicago | Charger delivery | Infra Mgr | Planned
Phase 2 | Q4 2026 | 60 | 35 | Partial | Ohio → Indiana | Grid permit | Procurement | On Track
Phase 3 | 2027 + | 40 | 20 | Yes | Minnesota → Detroit | Transformer upgrade | Ops Lead | Pending
Totals |  | 150 | 80

## Financial Model Summary
Metric | Unit | Pilot Actual | Scale Forecast | % Change vs Pilot | Source
Avg TCO per km | USD/km | 1.28 | 1.12 | -12.5% | TCO Tool
Energy Cost | USD/kWh | 0.24 | 0.18 | -25% | Load Forecast Tool
Utilization | % of fleet active | 82% | 90% | 9.756% | Fleet Telemetry
CO₂ Reduction | tCO₂ / yr | 1000 | 5600 | 460% | CO₂ Dashboard
ROI Period | years | 5.8 | 4.6 | -20.69% | Finance Lead

## Risk Register & Dependencies
Risk ID | Category | Description | Likelihood (H/M/L) | Impact (H/M/L) | Score | Mitigation | Owner | Status
R-01 | Infra | Utility permit delay | H | H | 9 | Pre-submit apps in parallel | Infra Mgr | Open
R-02 | Ops | Shift overlap charging | M | M | 4 | Dynamic load management test | Ops Lead | In progress
R-03 | Finance | CapEx escalation | M | H | 6 | Lock-in pricing for Q2 | Finance BP | Open

## Executive Dashboard
KPI | Target | Actual | Status
Overall Readiness | ≥ 80 % | 59.18% | 🟢
Total Fleet Deployed | 150 | 110 | 🟡
Key Risks Open | ≤ 3 | 2 | 🟠