## Overview
Field | Description | Example
Site Name / Code | Unique facility name or ID | MBR-01 (Rotterdam Depot)
Region / Country | Country or cluster | EU / Netherlands
Assessed by | Name, department | Site Ops / Engineering
Date of Assessment | dd/mm/yyyy | 2025-10-28
Assessment Status | Auto output (formula-driven) | Ready
Linked SOPs | 2.2 Procurement / 2.3 Site Readiness |  | Ready
Next Action Owner | Who to resolve gaps | Procurement Lead / Facilities | Partial
Not ready

## Site assessment checklist
Section | Key Checks | Status | Comments | Evidence Link
1. Site & Ownership | Landlord consent confirmed ✔️ Lease permits infrastructure changes ✔️ Maersk has right to build ✔️ | ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No
2. Grid & Power | Transformer kVA confirmed ✔️ Contracted capacity known ✔️ Peak load alerts reviewed ✔️ Spare capacity (≥20%) ✔️ | ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No
3. Layout & Access | Charger locations marked ✔️ Safe turning radius for trucks ✔️ Trenching route accessible ✔️ No conflict with fire exits / HGV movement ✔️ | ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No
4. Permitting & Civil Works | Permit types identified ✔️ Local authority lead times known ✔️ Drainage / ground conditions confirmed ✔️ Stormwater / paving checks complete ✔️ | ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No
5. Safety & HSSE | Electrical risk assessment complete ✔️ Earthing points identified ✔️ Emergency cut-off location marked ✔️ HSSE inspection done ✔️ | ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No ☐Yes / ☐Partial / ☐No

## Power and load data
Parameter | Value | Unit | Source / Owner
Contracted grid connection | 500 | kW | Utility / Energy Mgr
Transformer rating | 800 | kVA | Site Engineering
Average daily load | 400 | kW | Energy meter
Available headroom | 100 | kW | Calculation
Voltage level | 400 | V | LV
Phase type | 3
Planned EV load (Phase 1) | 60 | kW | Charging model
Grid upgrade required? | Yes/No |  | Utility confirmation

## Risk and mitigation log
Risk Category | Description | Likelihood | Impact | Mitigation / Next Action | Owner
Grid | Transformer upgrade required | High | High | Engage DSO early | Utility Lead
Civil | Drainage conflict at trench path | Medium | Medium | Modify route | Contractor
Permit | Landlord approval pending | Medium | High | Schedule review meeting | Site Manager

## Site layout plan
Site layout plan (PDF or AutoCAD export) Photos of proposed charger areas Access roads and transformer cabinet HSE signage zones

## Approval
Function | Reviewer | Date | Signature | Comments
Procurement
Facility
HSSE
Engineering